## To Do List
Task | Assigned To | Date Created | Date Started | Date Finished
Research continous integration options | Curtis | 2014-01-09
Build some project reporting template options | Curtis | 2014-01-09
Android Testing Frameworks | Sajid | 2014-01-09
Create some sample testing documentation templates (test plan, test cases) | Sajid | 2014-01-09
Build ER Models for the database | Peter | 2014-01-09
create some sample Use Case documentation Templates | Ben | 2014-01-09
Managing our To Do List | Ben | 2014-01-09
Animation, Canvas | Taylor | 2014-01-09
Start specing out architecture models and template | Chris | 2014-01-09
UI Design and screen mock ups | Kuba | 2014-01-09
Research AI options (minimax) | James | 2014-01-09
Talk with Prof. W. about scheduling regular meetings | Curtis | 2014-01-09
Talk with Prof. W. about making the GitHub repo public | Curtis | 2014-01-09

## Team Capacity Calculations
2014-01-09 | start
2014-03-27 | finish
2014-04-04 | last day of class
77 | work days
11 | work weeks
8 | # of people
6 | hours/week/person
528 | hours
144 | 1st iteration
144 | 2nd iteration
144 | 3rd iteration
48 | 4th iteration
480 | TOTAL